## Slide 1: Product Backlog
Textbook:
Ch. 6

## Slide 2: Product Backlog
PBI types (extended list)
  Feature (User Story)
  Change
  Defect
  Internal (Technical) improvement
  Knowledge acquisition

## Slide 3: Good PBI characteristics
D
E
E
P

## Slide 4: Good PBI characteristics
Detailed appropriately
Emergent
Estimated
Prioritized

## Slide 5: Grooming the PB
Name/define three grooming activities
  Hint: DEEP concepts
Who makes the decisions?
  Who else is involved?
  When is it done?
It depends . . .
Continuously?
During sprint review?

## Slide 6: Definition of Ready
Ensure top PBI’s are good enough to take action on (to be worked on in a sprint)
  Business value articulated
  Details understood
  No blocking dependencies
  Small enough
  Acceptance criteria

## Slide 7: Estimation in Scrum
Estimation target | Size unit
Product backlog item (PBI) | 
Task | 
Fill in the blanks
PBIs are estimated in Story points
Tasks are estimated in hours

## Slide 8: Estimation Practices
  Estimate as a team
  Estimates are not commitments
  Focus on accuracy, not precision
  Use relative versus absolute sizes
  … and why is each important?

## Slide 9: Planning Poker
What is this all about?
Consensus
Expert opinion
Discussion
Relative size
Accurate grouping
Use of history
Why do we do it?
Why the funny values? 1/2, 1, 2, 3, 5, 8, 13, 20, 40, ...

## Slide 10
0 - the item is already done or is so trivial it doesn't warrant giving it a finite value; for example, correcting the spelling on a button from “quite” to “quit”. Used for fixing trivial defects.
1/2 - a tiny item - perhaps a minor defect fix, such as catching an otherwise uncaught exception.
1,2,3 - small defects, knowledge acquisitions, or stories that might take from 1 to several hours to fix, research, or implement.
5,8,13 - medium stories (not defects or knowledge acquisition, unless a significant re-write or amount of research is needed).
  A 13 is the largest single story that could be completed within a sprint. Anything larger must be broken down into smaller stories.
20, 40 - significant features that would take longer than a sprint to implement
100 - huge sets of features (comprising an entire product release)
infinity - obviously too big to even guess at without further detailed discussion
? - the defect or story under consideration needs further discussion - not enough is known about the story or defect to make sense of it or provide an estimate. More discussion is needed.
pi - not used in SE2800, since you won't be doing day-long or multi-day spring grooming. Used to indicate a break is needed during a multi-hour planning session.
Story points

## Slide 11: Estimation Exercise
In your team:
  Choose a PBI to estimate
  Discuss the item
  Each estimator privately chooses a card
  Show all cards at once
  Check for consensus; repeat if none

## Slide 12: Checkpoint
Turn to your partners…
What is good about Scrum planning?
What seems not so good?
What questions do you have?

## Slide 13: Playing Planning Poker
In your team:
  Choose a PBI to estimate
  Discuss the item
  Each estimator privately chooses a virtual card
  Show all cards at once
  Check for consensus; discuss and repeat if none
Planningpoker.com
  You can use this site to “play” if you want

## Slide 14: Planning
For User stories 1 and 2 (or 3 or 4 or 5) (the ones you are already implementing)
  For tasks as well as any defects
  Come up with a story point estimate using planning poker
Add up the story points and enter it as the new issue weight, you may add a note to the end of a task about it weight contribution if you like.

## Slide 15: Review
Product Backlog Items
Item types used at MSOE
Characteristics of PBIs: DEEP
Grooming, ensuring PBIs are ready
Estimation: Planning Poker

## Slide 16: UI Testing in Java
Assumption: painful but readily available
Research: lots of vaporware, abandonware
  Many solutions for web, but not a lot for Java
  FrogLogic, RAutomation, MarathonTesting, UISpec4J, Mspec, abbot
Method that works:
  JavaWorld TestUtils; see also counter.zip

## Slide 17: UI Testing in Java
Each component: call .setName with unique string
Test code:
TestUtils.getChildNamed(frame, name-of-child)
Use .doClick, .value(), etc. to exercise code
Robust
  Doesn’t depend on screen locations, specialized test frameworks
  But no auto-capture/replay