## Slide 1: Metrics and Velocity
Textbook:
Ch. 7

## Slide 2: Software Product Measures/Metrics
Design Complexity
  Algorithmic, architectural, data flow
Code Complexity
  Size (Function Pts, SLOC, Modules, Subsystems, Pages, Documents )
Deliverable Quality
  Correctness, Maintainability, Reliability, Efficiency, Usability, Flexibility, Testability, Portability, Reusability, Availability, Complexity, Understandability, Modifiability
  Error density ( errors/ SLOC )
  Defect density ( defects/ SLOC or defects/ FP )

## Slide 3: SLOC vs. FP
Relationship between lines of code and function points depends upon
  the programming language
  the quality of the design
Empirical studies show an approximate relationship between SLOC and FP

## Slide 4: SLOC/FP (average)
Assembly language 320
C 128
COBOL, FORTRAN 106
C++ 64
Java 55
Visual Basic 32
Smalltalk 22
SQL 12
Graphical languages (icons) 4
http://www.qsm.com/resources/function-point-languages-table

## Slide 5: What’s a metric?
It measures something, like:
  The software product
    Its quality
    Its degree of completeness, so far
    Its suitability for some use
  The process and people creating it
    How close to “on plan” are we?
    Tracking how the team is working
    Or what our test coverage is
    Or how we are cutting risks
It’s a number, a measure, vs some standard
  Like “burndown” or “velocity”

## Slide 6: The Cone of Uncertainty
4x |  |  |  |  |  |  |  |  |  | 
2x |  |  |  |  |  |  |  |  |  | 
1.5x |  |  |  |  |  |  |  |  |  | 
1.25x |  |  |  |  |  |  |  |  |  | 
1.0x |  |  |  |  |  |  |  |  |  | 
.8x |  |  |  |  |  |  |  |  |  | 
.67x |  |  |  |  |  |  |  |  |  | 
.5x |  |  |  |  |  |  |  |  |  | 
25x |  |  |  |  |  |  |  |  |  | 
Estimate of Variability
Initial Concept
Software Complete

## Slide 7: Team Velocity
Velocity is the number of story points per sprint completed
You calculate velocity to predict how much work to commit to in a sprint
  Velocity only works if you estimate your story points consistency
Over time you will know: team has a velocity of 32 story points per sprint
  Over time this will self-correct
  Over time you will be able to predict the project schedule (and release)

## Slide 8: Calculating Team Velocity
Select a regular time period (sprint) over which to measure velocity
Add up the story point estimates for 100% completed stories
At the end of the sprint, the figure you have is your velocity
You can then use your velocity as a basis for your future commitments

## Slide 9: Re-estimation
As you complete more sprints, velocity changes
  Velocity changes because of minor inconsistencies in the story point estimates
  Team velocity will typically stabilize between three and six iterations
Re-estimation of the entire project happens after each sprint
  New velocity
  New story points added and removed (completed)
  Use the cone!

## Slide 10: Planning Poker
What is this all about?
Consensus
Expert opinion
Discussion
Relative size
Accurate grouping
Use of history
Why do we do it?
Lets try this out!
Why the funny values? 1/2, 1, 2, 3, 5, 8, 13, 20, 40, ...

## Slide 11: Playing Planning Poker
In your team:
  Identify the PBI to estimate
  Discuss the item
  Each estimator privately chooses a virtual card
  Show all cards at once
  Check for consensus; discuss and repeat if none
Planningpoker.com

## Slide 12: Keys to velocity
Can velocity be compared between teams?
  Story points are not comparable between teams!
Can sprints have different lengths?
  No! This makes velocity to be a useless metric
  The only time to vary sprint length: team needs to experiment with different models
  NEVER extend a sprint “just to complete one more story”!
What if get to end of sprint backlog before the end of the sprint?
  Simply pick up the top PBI and start to work – keep moving forward!
  No commitment to finish this!
  This is why a sprint’s worth of PBIs should be at the top of the Product Backlog at all times!

## Slide 13: Review
Metrics: measurements of a team’s effectiveness
  SLOC: possibly useful at a developer level; generally not comparable between developers
  Function Points: a more robust measure
  Story Points: very useful within a team
Velocity: story points/sprint
  Increases in velocity is a worthwhile team goal
  Process improvement is a key element of Scrum, so velocity is important!
  Not comparable between teams
  Relies on consistent sprint lengths