## Slide 1: Scrum
SWE 2710

## Slide 2: Classical software development
Requirements: talking to customer
Design: How to implement requirements
Implementation: coding
Verification: testing
Maintenance: fixing
Justification:
Simple
Covers all necessary products
Known as waterfall model:
Water gently flowing down hill towards a goal…
But what happens if discover a problem?
Is this really more like Niagara Falls?
Not agile – doesn’t respond to change well
So why was this ever used?

## Slide 3: The case for plan-driven development
Consider the A380
          5000+ ft2 floor space, up to 853 passengers, $4e8 a plane
          Thousands of engineers
          Some planning may be helpful!

## Slide 4: The case for agile
The problem with planning: estimation
  Estimation is hard!
  Get better with experience, but it’s still hard
  Customers rarely know what they want up front
Agile
  Develop the plan as you go
  Be more responsive
  But how can this work?
Many agile methods
  Kanban (motivated by manufacturing)
  Extreme programming – because who wouldn’t want to be an extreme programmer
  The method we study in 2710: Scrum
Notes: Picture from https://www.givemesport.com/most-agile-nfl-players-all-time/ (captured Feb, 2026)

## Slide 5: Why the name “scrum”?
Origin of term: rugby football
  Scrum: restarts game after interruption
  Players struggle to gain possession of ball tossed between teams
Folks working together to solve shared problem; no leaders
  Key difference: no opposing team!

## Slide 6: Scrum has been used by:
Microsoft
Yahoo
Google
Electronic Arts
Lockheed Martin
Philips
Siemens
Nokia
IBM
Capital One
BBC
Intuit
Nielsen Media
First American Real Estate
BMC Software
Ipswitch
John Deere
Lexis Nexis
Sabre
Salesforce.com
Time Warner
Turner Broadcasting
Oce
Notes: 6

## Slide 7: Scrum has been used for:
Commercial software
In-house development
Contract development
Fixed-price projects
Financial applications
ISO 9001-certified applications
Embedded systems
24x7 systems with 99.999% uptime requirements
the Joint Strike Fighter
Video game development
FDA-approved, life-critical systems
Satellite-control software
Websites
Handheld software
Mobile phones
Network switching applications
ISV applications
Some of the largest applications in use
Notes: 7

## Slide 8: Scrum Basics: project = Si=1..n sprinti
If you find videos useful:
  http://www.youtube.com/watch?v=D8vT7G0WATM

## Slide 9: History of Scrum
1995:
  analysis of common software development processes  not suitable for empirical, unpredictable and non-repeatable processes
  Design of a new method: Scrum by Jeff Sutherland & Ken Schwaber
  Enhancement of Scrum by Mike Beedle & combination of Scrum with Extreme Programming
1996:
  introduction of Scrum at OOPSLA conference
2001:
  publication “Agile Software Development with Scrum” by
  Ken Schwaber & Mike Beedle
Successful appliance of Scrum in over 50 companies
Founders are members in the Agile Alliance
83% of companies use Scrum or a variant today!
Notes: Successful = increase in productivity, satisfied/ happy team

## Slide 10: Scrum – a lightweight, agile process
Key goals:
  Iterative, incremental process
  Team-based approach
  developing systems/ products with rapidly changing requirements
  Controls the chaos of conflicting interest and needs
  Improve communication and maximize cooperation
  Protecting the team form disruptions and impediments
  A way to maximize productivity
Developed in the 1990s, became the default process by about 2010

## Slide 11: Sequential vs. overlapping development
Rather than doing all of one
thing at a time...
...Scrum teams do a little of
everything all the time
Requirements
Design
Code
Test
Notes: 11

## Slide 12: Scrum framework
Product owner
ScrumMaster
Developers
Roles
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts
Notes: 12

## Slide 13: Product owner
Define the features of the product
Decide on release date and content
Be responsible for the profitability of the product (ROI)
Prioritize features according to market value
Adjust features and priority every iteration, as needed
Accept or reject work results
Notes: 13

## Slide 14: The ScrumMaster
Represents management to the project
Responsible for enacting Scrum values and practices
Removes impediments
Ensure that the team is fully functional and productive
Enable close cooperation across all roles and functions
Shield the team from external interferences
Notes: 14

## Slide 15: Developers
Typically 5-9 people
  May include ScrumMaster as developer
Cross-functional:
  Programmers, testers, user experience designers, etc.
Members should be full-time
  May be exceptions (e.g., database administrator)
Teams are self-organizing
  Ideally, no titles
Membership should change only between sprints
Notes: 15

## Slide 16: Scrum framework
Product owner
ScrumMaster
Developers
Roles
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts
Activities done each sprint
Notes: 16

## Slide 17: Sprint Planning Meeting
Activities spread throughout sprint
  Identify items to put on the product backlog
    Product Backlog Items: PBIs
  Refine those items: ensure the stories are sprintable
  Estimate their size
Start of sprint
  Product owner: identify highest priority items
  Team: Finalize any details
  Identify sprint goal: where are we headed?
Sprint starts
  With work to be done
  Note: tasks NOT assigned – the sprint backlog belongs to the team
  You may know who will do certain PBIs at start, but
  Anyone can pick up an item that is not started...

## Slide 18
Sprint planning meeting
Sprint prioritization
Analyze and evaluate product backlog
Select sprint goal
Sprint planning
Decide how to achieve sprint goal (design)
Create sprint backlog (tasks) from product
backlog items (user stories / features)
Estimate sprint backlog in hours
Sprint
goal
Sprint
backlog
Business conditions
Team capacity
Product backlog
Technology
Current product
Notes: 18

## Slide 19: Lets try it
The product owner wants you to create a sandwich for her restaurant
The product backlog contains the following items (ranked):
  Find recipe
  Purchase ingredients
  Combine ingredients
  Test for quality (eat)
  Refine recipe to maximize profitability
  Refine recipe to maximize enjoyability
  Solve world hunger
Put these items on post-it notes for your team on a whiteboard
Lets do the “before lunch” part of the meeting together…
  Creating/updating Product Backlog
  Determining the Sprint Goal
  Participants: Product Owner, Scrum Master, Scrum Team

## Slide 20: Sprint planning- 2nd part
Team selects items from the product backlog
they can commit to completing
Sprint backlog is finalized
  Tasks are identified and each is estimated
    Each team member develops and estimate and they are compared
    all at once during the meeting to determine the group estimate
  Collaboratively, not done alone by the ScrumMaster
High-level design is considered
As a vacation planner,
I want to see photos of
the hotels.
Code the middle tier (8)
Code the user interface (4)
Write test fixtures (4)
Code the foo class (6)
Update performance tests (4)
Notes: 20

## Slide 21: Lets try it
Do the “after lunch” part in your team
  Creating/updating Sprint Backlog
  Participants: Scrum Master, Scrum Team
Create the sprint backlog using post-it notes!
  Don’t forget to include effort estimates and team assignments
    Each team member should have a task
    Everyone volunteers for tasks (no forced assignments)

## Slide 22: The daily scrum
Parameters
  Daily
  15-minutes
  Stand-up
  Focused on development tasks
  Only include folks involved in development
Not for problem solving
  Solve problems in small groups after the meeting
Helps avoid other unnecessary meetings
Notes: 22

## Slide 23: Everyone answers 3 questions
These are not status for the ScrumMaster
They are commitments in front of peers
What did you do yesterday?
1
What will you do today?
2
Is anything in your way?
3
Notes: 23

## Slide 24: The sprint review
Team presents what it accomplished during the sprint
Typically takes the form of a demo of new features or underlying architecture
Informal
  2-hour prep time rule
  No slides
Whole team participates
Invite the world
We will do these during class
Notes: 24

## Slide 25: Sprint retrospective
Periodically take a look at what is and is not working
Typically, ~15 minutes
Done after every sprint
Whole team participates
  ScrumMaster
  Product owner
  Developers
  Typically, NOT other clients, managers
Notes: 25

## Slide 26: Sprint Retrospective
Start / Stop / Continue
Whole team gathers and discusses what they’d like to:
Start doing
Stop doing
Continue doing
This is just one
of many ways
to do a sprint
retrospective.
Notes: 26

## Slide 27: Scrum framework
Product owner
ScrumMaster
Developers
Roles
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts
Documenting the process
Notes: 27

## Slide 28: Product backlog
The requirements
  Typically, user stories
  Also: defects, design improvements
A list of all desired work on the project
Each must have value
Prioritized by the product owner
Reprioritized at the start of each sprint
Product backlog = S PBI
Notes: 28

## Slide 29: A sample product backlog (for a hotel reservation system)
Backlog item
Estimate
Allow a guest to make a reservation
3
As a guest, I want to cancel a reservation.
5
As a guest, I want to change the dates of a reservation.
3
As a hotel employee, I can run RevPR reports (revenue-per-room)
8
Improve exception handling
8
...
30
...
50
Notes: 29

## Slide 30: The sprint goal
A short statement of focus of sprint for work
Database Application
Financial services
Life Sciences
Support features necessary
for population genetics studies.
Support more technical indicators than company
ABC with real-time, streaming data.
Make the application run on SQL Server in
addition to Oracle.
Notes: 30

## Slide 31: Managing the sprint backlog
Individuals pick PBIs (with discussion w/ team)
  not assigned by external agents
Estimated work remaining updated daily
Only team members can add, delete or change the sprint backlog (not the product owner)
If work is unclear, define a sprint backlog item with increased time
  Break it down later
PBI = collection of tasks
  Each task: max 4-10 hours
Notes: 31

## Slide 32: Sprint Burndowns
Progress over sprint
Here: long period with no PBIs completed
Challenging for PO: too much suspense
Better: smooth progress
Prefer to not see: line going up!
Not a substitute for reviews, discussion

## Slide 33: Scrum Scalability
Typical individual team is 7 ± 2 people
  Scalability comes from teams of teams
Factors in scaling
  Type of application
  Team size
  Team dispersion
  Project duration
Scrum has been used on multiple 500+ person projects
Notes: 33

## Slide 34: Scaling Scrum

## Slide 35: Scrum Overview
Roles
  Product owner
  ScrumMaster
  Developers
Ceremonies
  Sprint
  Sprint Planning
  Daily Scrum Meeting
  Review
  Retrospective
Artifacts
  Product backlog/PBI
  Sprint Backlog
  Burndown charts
Review/retrospective

## Slide 36: Scrum Overview
Roles
  Product owner
  ScrumMaster
  Developers
Ceremonies
  Sprint
  Sprint Planning
  Daily Scrum Meeting
  Review
  Retrospective
Artifacts
  Product backlog/PBI
  Sprint Backlog
  Burndown charts
Review/retrospective
Manage ceremonies; remove impediments
What will be developed, and in what order
5-9 people: determine how to deliver what
product owner requests