## Slide 1: Questions?
Cycle 1
Process details
Process Dashboard
Coding vs. Testing
???

## Slide 2: We have already discussed the overall PSP planning process.
Define requirements
Make conceptual design
Estimate size
Estimate effort
Produce schedule
Develop product
Analyze data
Resources available
Productivity database
Size database
But how exactly do we do this part?
We can correct an estimate by using regression with historical data, but how do we make the estimate in the first place?

## Slide 3: Conceptual Design vs. Detailed Design
  Developed in for
    Understanding requirements
    Identifying objects/elements that provide necessary functionality
  Used only to make estimates
    A conceptual design should provide enough guidance for estimating, but not get too deeply into the actual design work.
Conceptual designs are for planning, and may not represent the final detailed design chosen for a project.

## Slide 4: Conceptual Design vs. Detailed Design
Detailed design
  Developed in design phase
  Usually based on conceptual design
    May modify or even replace it
  Used for code basis

## Slide 5: In software, as in building construction, resources and size are often correlated, but how do we make the initial size estimate?
The floor area (square feet) often correlates well with the actual construction cost, but may be difficult to determine from an early design.
A proxy measure, like the number and relative size of the rooms, may work better for initial planning.

## Slide 6: The conceptual design consists of a set of proxy Parts, each usually consisting of a number of Items
Proxy Examples |  | 
Context | Parts | Items
Java, C++ | Classes | Methods
Website | Pages | Forms
C, assembly | Modules | Functions
Database | Tables | Columns
Book | Chapters | Sections

## Slide 7: To make a proxy-based estimate, we combine historical data with a conceptual design.
The planning process is outlined in the planning script.
Type of class | Average LOC per item (method) |  |  |  | 
 | VS | S | M | L | VL
Calculation | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
Data | 2.60 | 4.79 | 8.84 | 16.31 | 30.09
I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
Text | 3.75 | 8.00 | 17.07 | 36.41 | 77.66

## Slide 8: To make a proxy-based estimate, we combine historical data with a conceptual design.
Type of class | Average LOC per item (method) |  |  |  | 
 | VS | S | M | L | VL
Calculation | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
Data | 2.60 | 4.79 | 8.84 | 16.31 | 30.09
I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
Text | 3.75 | 8.00 | 17.07 | 36.41 | 77.66
Part (class) | Type | # Items | Rel size | Avg size (from table) | Part size
Matrix | Data | 13 | M | 8.84 | 115
EqnSolver | Calc | 8 | L | 24.7 | 197
DataStore | Data | 3 | L | 16.3 | 49

## Slide 9: An obvious question: where does the relative-size table come from?
Initially, we don't have one!
  For Java, we start out with Humphrey's C++ table
    Based on accumulated historical data
Type of class | Average LOC per item (method) |  |  |  | 
 | VS | S | M | L | VL
Calculation | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
Data | 2.60 | 4.79 | 8.84 | 16.31 | 30.09
I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
Text | 3.75 | 8.00 | 17.07 | 36.41 | 77.66

## Slide 10: Percentile Method Example
Part# | Items | Total size | Size/item
1 | 3 | 18 | 6.00
2 | 3 | 18 | 6.00
3 | 3 | 25 | 8.33
4 | 3 | 31 | 10.33
5 | 3 | 37 | 12.33
6 | 5 | 82 | 16.40
7 | 4 | 82 | 20.50
8 | 4 | 87 | 21.75
9 | 4 | 89 | 22.25
10 | 10 | 230 | 23.00
11 | 3 | 85 | 28.33
12 | 3 | 87 | 29.00
13 | 10 | 558 | 55.80
M (median)
VS (min)
VL (max)
S (25th %)
L (75th %)

## Slide 11: Getting Category-Size Data
Text, page 133
VS
VL
L
S
M

## Slide 12: When size and time measures correlate adequately, we can use a size estimate to make a time estimate.
A similar approach allows estimation of overall development time based on proxy size estimate (using a different set of regression parameters).

## Slide 13: When size and time measures correlate adequately, we can use a size estimate to make a time estimate.
Size
Estimated Time
Data points for previous development cycles

## Slide 14: In the Process Dashboard, we normally use a wizard to make size and time estimates.

## Slide 15: When the wizard completes, the estimating parameters and results are displayed in the size estimating template.
The available historical data may limit the choice of estimating methods; we'll discuss this in more detail later.

## Slide 16: Advantages of using a defined estimating method
You have known practices that you can work to improve
It provides a framework for gathering estimating data
By using consistent methods and historical data, your estimates will become more consistent