## Slide 1: Process Adaptations

## Slide 2: “The process is your servant. If it does not help you, you must change it.” - Watts Humphrey
No single "canned" software development process can meet the needs of all software engineers and their organizations.

## Slide 3: …but you can’t modify a process until you have experience using one
The objective is for software engineers, and especially teams, to define and improve their own processes.
However, it is very difficult to define a usable personal or team process until they have experience in working within one.
A major goal of the initial "PSP" process is to provide experience and a basis for process development – NOT to try to tell you that this particular process is the only acceptable way of working
“If you don’t know where you are, a map won’t help”
- Humphrey

## Slide 4: However, Humphrey suggests that the following critical components should be used for any process:
Scripts: Describe process steps, entry/exit criteria, etc.
Forms: Framework for gathering, retaining, and analyzing process data.
Standards: Guide your work and provide a basis for verification and quality management
PIPs: Identify/record process issues and generate/validate potential solutions

## Slide 5: The process we have used so far is reasonable for small software development increments with well defined requirements.
For an individual software engineer in a development organization you’re familiar with:
  What aspects of the "PSP" process could be used with little change?
  What modifications would be required?
Plan
Design
DLDR
Code
CR
Test
PM

## Slide 6: Teams and engineers can create custom development processes.

## Slide 7: Custom forms and scripts can be developed to support new processes. (ref: Dr. Sebern)

## Slide 8: Custom processes can support requirements and architecture/design work.

## Slide 9: Process Dashboard supports task and schedule planning for individual engineers and teams

## Slide 10: Review: The Planned Value (PV) of each task is the percentage it represents of the total planned project time.
Task | Plan hrs. | PV% | Cum. hrs. | Cum. PV% | Plan wk.
A | 10 |  |  |  | 
B | 8 |  |  |  | 
C | 7 |  |  |  | 
D | 3 |  |  |  | 
E | 9 |  |  |  | 
Total | 37 |  |  |  | 
27.0
21.6
18.9
8.1
24.3
100
10 | 27.0
18 | 48.6
25 | 67.6
28 | 75.7
37 | 100.0
1
3
3
4
5

## Slide 11: Earned value (EV) represents the cumulative planned value of completed tasks, even if they are not completed in the planned sequence.
Week | Task | PV% | EV% | Cum. EV
1 | A |  |  | 
 | D |  |  | 
2 | B |  |  | 
3 | -- |  |  | 
4 | C |  |  | 
5 | -- |  |  | 
6 | E |  |  | 
27.0 | 27
8.1 | 
21.6 | 21.6
-- | --
18.9 | 18.9
-- | --
24.3 | 24.3
27
56.7
56.7
75.6
75.6
 100.0

## Slide 12: Looking at Plan vs Earned value can help identify problems in the plan.
Adapted from Willet (SEI), Boston SPIN talk, 2004

## Slide 13: Tracking time/effort can help uncover problems
Work hours on target
Completed tasks show severe underestimates
Detail tasks log shows most of problem is in Unit Test
Defect Fix Time by type shows main problem is legacy system defects

## Slide 14: Process Dashboard can generate earned value charts and forecasts.

## Slide 15: What kind of process would you use when you don't know what you are doing?
Suppose your next project is in a new language and development environment. You are not familiar with the available libraries and tools. What effect will this have on your process?
One approach: Prototype Experimental Process (PEP)
Experiment until you get something working
Document the design of your prototype
Review the design
Update and/or refactor the code
Review the updated code
Test / inspect
Repeat as needed

## Slide 16: Have you ever heard of “agile” processes or methods? What does the team mean to you?

## Slide 17: A common issue is how to integrate an incremental development process with up-front requirements and design documentation.
"Big design up front"
"We don't need no stinkin' process“
It's not very helpful to view this "conflict" as a cultural battle.
Lightweight, disciplined, data-driven process ("PSP/TSP" based?)

## Slide 18: There are twelve main practices in eXtreme Programming (XP)
Planning (what, when)
Metaphor (how it works)
Simple design
Testing (TFD/acceptance)
Refactoring
Small releases (monthly)
Pair programming
Collective ownership
Continuous integration
40-hour week
On-site customer
Coding standards
http://xprogramming.com/book/whatisxp/

## Slide 19: Another popular "agile" process is called "Scrum"
Backlog
  Collection of product requirements (features)
  Prioritize those to be implemented in the current “Sprint”
Sprint (tasks to be done)
  Short iterations (4 wks)
  Sprint planning session
    Burn-down chart (Mirror image of EV)
Scrum
  Daily meeting (“daily standup”)
  Determines what’s done/not done; aimed at removing obstacles to completion
Sprint planning session
  Burn-down chart
    Mirror image of EV
Sprint retrospective
  PIPs

## Slide 20: Here is an example of one attempt to integrate agile/TDD practices with "TSP" processes
Time logging (no timer)
  At least twice a day
    Before Lunch
    Before going home
Initial phases
  Requirements
  Architecture/Design
Agile Increments:
  Code/test/design
    In "design" phase
  Document the design
    Reviewable form
  Review/inspect design
  Code phase
    Completion, updates
  Unit testing (100% coverage)
  Code inspection
This was the original plan in 2006, but . . .

## Slide 21: After about a year (2007), this organization decided to modify the "agile/TSP" process.
Design
Design review
Design inspection
Production code + unit test coding
Production code + unit test review
Production code + unit test inspection
Build and unit test
Heavy reliance on automated testing
Create a new test whenever a defect escapes the test suite
Designs must be testable
www.sei.cmu.edu/tsp/symposium/